## How to use
Self build budget template
Free from Self Build Budget, built by first-time self builders. selfbuildbudget.com
How it works
1. Budget: for each line, type a low and a high figure. The high figure is your planning figure. Add or rename lines as you need.
2. Quotes: record every quote against a budget line. Put Y in Accepted once you accept it.
3. Payments: record every invoice you pay, with the amount before VAT and the VAT separately.
4. Summary: shows your planning total, contingency, accepted quotes, paid, projected and remaining, overall and by stage.
Which cells to edit
Only the cells shaded pale yellow. Everything else is worked out for you.
The first row on the Quotes and Payments sheets is an example (shaded green). Overwrite it or delete it.
How the figures work
All budget, quote and payment totals are what you actually pay, including any VAT you're charged. Any VAT you reclaim comes back after completion.
Projected cost for a line = once you've accepted a quote, the larger of the accepted quotes and what you've paid. Until then, the larger of your high figure and what you've paid.
Remaining = projected cost minus paid (never below zero).
Over/under = projected cost minus your high figure. A positive number means pressure on that line.
Contingency is a separate pot, set as a percentage of the planning total on the Summary sheet.
This template is a starting point, not financial or tax advice. For VAT reclaim questions speak to a qualified adviser.
Want this done for you, with quotes, payments and VAT tracked live on your phone? Start a free estimate at https://my.selfbuildbudget.com

## Summary
Where we stand
Contingency (% of planning total) | 10% | Lenders often look for 7% to 15% (Harpenden Building Society self build guide). Change to suit your project.
Planning total (sum of high figures) | 0
Contingency | 0
Planning total with contingency | 0
Accepted quotes | 38500
Paid so far | 5040
Projected cost | 43540
Still to pay (projected minus paid) | 38500
Projected against planning total with contingency | -43540 | Positive = headroom left. Negative = projected to overspend, even after contingency.
VAT paid so far | 840
VAT marked possibly reclaimable | 840
By stage
Stage | High, planning figure (£) | Accepted quotes (£) | Paid (£) | Projected (£) | Over/under vs high (£)
Design, fees and surveys | 0 | 0 | 0 | 0 | 0
Site set-up and groundworks | 0 | 38500 | 0 | 38500 | 38500
Foundations | 0 | 0 | 5040 | 5040 | 5040
Superstructure | 0 | 0 | 0 | 0 | 0
Roof | 0 | 0 | 0 | 0 | 0
Windows and external doors | 0 | 0 | 0 | 0 | 0
First fix | 0 | 0 | 0 | 0 | 0
Insulation and plastering | 0 | 0 | 0 | 0 | 0
Second fix | 0 | 0 | 0 | 0 | 0
Kitchen and bathrooms | 0 | 0 | 0 | 0 | 0
Finishes | 0 | 0 | 0 | 0 | 0
Utilities and connections | 0 | 0 | 0 | 0 | 0
External works | 0 | 0 | 0 | 0 | 0
Lines you add with a new stage name show on the Budget sheet but not in this table; add the stage name here to include it.

## Budget
Stage | Line | Low (£) | High, planning figure (£) | Accepted quotes (£) | Paid (£) | Projected (£) | Remaining (£) | Over/under vs high (£) | Notes
Design, fees and surveys | Architect and design |  |  | 0 | 0 | 0 | 0 | 0
Design, fees and surveys | Structural engineer |  |  | 0 | 0 | 0 | 0 | 0
Design, fees and surveys | Surveys and investigations |  |  | 0 | 0 | 0 | 0 | 0
Design, fees and surveys | Planning and building control fees |  |  | 0 | 0 | 0 | 0 | 0
Design, fees and surveys | Warranty and site insurance |  |  | 0 | 0 | 0 | 0 | 0
Site set-up and groundworks | Site set-up and welfare |  |  | 0 | 0 | 0 | 0 | 0
Site set-up and groundworks | Groundworks and drainage |  |  | 38500 | 0 | 38500 | 38500 | 38500
Foundations | Foundations |  |  | 0 | 5040 | 5040 | 0 | 5040
Superstructure | Frame or walls |  |  | 0 | 0 | 0 | 0 | 0
Superstructure | Floors and stairs |  |  | 0 | 0 | 0 | 0 | 0
Roof | Roof structure and covering |  |  | 0 | 0 | 0 | 0 | 0
Roof | Gutters and rainwater |  |  | 0 | 0 | 0 | 0 | 0
Windows and external doors | Windows and external doors |  |  | 0 | 0 | 0 | 0 | 0
First fix | Electrics first fix |  |  | 0 | 0 | 0 | 0 | 0
First fix | Plumbing and heating first fix |  |  | 0 | 0 | 0 | 0 | 0
First fix | Ventilation |  |  | 0 | 0 | 0 | 0 | 0
Insulation and plastering | Insulation |  |  | 0 | 0 | 0 | 0 | 0
Insulation and plastering | Plastering |  |  | 0 | 0 | 0 | 0 | 0
Second fix | Electrics second fix |  |  | 0 | 0 | 0 | 0 | 0
Second fix | Plumbing and heating second fix |  |  | 0 | 0 | 0 | 0 | 0
Second fix | Joinery and internal doors |  |  | 0 | 0 | 0 | 0 | 0
Kitchen and bathrooms | Kitchen |  |  | 0 | 0 | 0 | 0 | 0
Kitchen and bathrooms | Bathrooms |  |  | 0 | 0 | 0 | 0 | 0
Finishes | Flooring |  |  | 0 | 0 | 0 | 0 | 0
Finishes | Decoration |  |  | 0 | 0 | 0 | 0 | 0
Utilities and connections | Water, power and other connections |  |  | 0 | 0 | 0 | 0 | 0
External works | Driveway and paths |  |  | 0 | 0 | 0 | 0 | 0
External works | Landscaping |  |  | 0 | 0 | 0 | 0 | 0
| Total | 0 | 0 | 38500 | 5040 | 43540 | 38500 | 43540

## Quotes
Date | Supplier | Stage | Budget line | Amount inc VAT (£) | Accepted? (Y/N) | What's included or excluded
2026-03-14 | Example Groundworks Ltd | Site set-up and groundworks | Groundworks and drainage | 38500 | Y | Excludes skip hire and soakaway test

## Payments
Date paid | Supplier | Invoice ref | Stage | Budget line | Amount before VAT (£) | VAT charged (£) | Total paid (£) | VAT possibly reclaimable? (Y/N)
2026-04-02 | Example Builders Merchant | INV-1043 | Foundations | Foundations | 4200 | 840 | 5040 | Y